## Execution Summary
NafaIQ User-Journey Test Execution Summary
Field | Value | Interpretation
Scope | Automated browser journeys only | Unit/API assertions were inventoried but do not change user-journey status.
Run | 2026-07-29 16:13:26 PKT | Local Playwright run against the demo user.
Branch / commit | tayyib · 50d88ee | Includes the router preload-race fix.
Journey results | 40 Pass · 8 Fail · 1 Blocked | 49 user-facing project executions; excludes the passing auth setup.
Runner results | 41 Pass · 8 Fail · 1 Skipped | Playwright includes one technical authentication setup.
Flaky | 0 | Local run used zero retries; CI retries twice.
HTML report | frontend/packages/e2e/reports/html/index.html | Screenshots, videos, traces, and step-level evidence.
JSON report | frontend/packages/e2e/reports/results.json | Machine-readable source for statuses and replay selection.
User-Journey Bug Focus
Bug ID | Area | Affected Experience | Observed User Impact | Status | Failed Executions
UJ-BUG-01 | Finance | Pixel 7 demo journey | A full-screen loading overlay blocks the Transactions tab, preventing search and validation journeys. | Open | 3
UJ-BUG-02 | Portfolio | Desktop and Pixel 7 demo journeys | Holding management cannot be started reliably because a visible Delete control is unavailable. | Open | 5
Discovered Automated Test Inventory
Layer | Files | Primary Focus | Used for Status Updates?
Playwright E2E | 7 | Real browser user journeys (6 specs + auth setup) | Yes — latest run is the status authority
Web Vitest | 17 | Components, hooks, stores, contracts | No — supporting technical coverage
Mobile Jest | 19 | Screens, components, hooks, clients | No — supporting technical coverage
Backend Pytest | 142 | API, domain, data, AI, admin behavior | No — supporting technical coverage

## E2E Journey Results
Execution ID | Area | Browser / User | User Journey | Preconditions | Reproduction Steps | Expected User Outcome | Actual Outcome | Status | Priority | Automation Source | Evidence | Run Commit | Run Time (PKT)
E2E-001 | Landing | Desktop Chrome · Anonymous | landing › renders the marketing page with its conversion affordances | Anonymous visitor; web and API servers available. | 1. Open /. 2. Confirm the page title and primary heading. 3. Locate the Try Demo action. | Landing page renders and exposes a clear demo conversion action. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/public/landing.spec.ts:11 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-002 | Authentication | Desktop Chrome · Anonymous | landing › offers a route into the auth page | Anonymous visitor on the landing page. | 1. Open /. 2. Select Sign In/Get Started. 3. Observe the destination. | Visitor reaches the authentication page without a broken transition. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/public/landing.spec.ts:19 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-003 | Plans | Desktop Chrome · Anonymous | landing › exposes the pricing page without a session | Anonymous visitor. | 1. Open /plans. 2. Confirm the pricing page identifies itself. | Pricing is available without requiring sign-in. | Journey completed and all user-facing assertions passed. | Pass | P2 | frontend/packages/e2e/tests/public/landing.spec.ts:31 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-004 | Authentication | Desktop Chrome · Anonymous | auth page › shows a usable credential form | Anonymous visitor. | 1. Open /auth. 2. Locate the email and password inputs. | A usable credential form is visible. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/public/landing.spec.ts:39 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-005 | Authentication | Desktop Chrome · Anonymous | auth page › keeps an anonymous visitor out of the dashboard | No authenticated session. | 1. Open /app directly. 2. Observe route handling. | Visitor is redirected to /auth and protected data is not displayed. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/public/landing.spec.ts:48 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-006 | Market | Desktop Chrome · Anonymous | PSX terminal › serves the terminal route | Anonymous visitor; local API available. | 1. Open /psx. 2. Confirm the terminal page title. | The public PSX terminal route renders. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/public/psx-terminal.spec.ts:16 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-007 | Market | Desktop Chrome · Anonymous | PSX terminal › renders the chart card, toolbar, plot and heatmap (needs the market-hours HAR) | Deterministic market-hours HAR fixture available. | 1. Open /psx. 2. Inspect chart card, controls, plot, and heatmap. | Core market visualizations are present and usable. | Blocked: the deterministic market-hours HAR fixture does not exist, so this data-dependent journey was intentionally not executed. | Blocked | P1 | frontend/packages/e2e/tests/public/psx-terminal.spec.ts:38 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-008 | Stock Detail | Desktop Chrome · Anonymous | stock detail › opens a symbol by deep link | HBL is a valid symbol. | 1. Open /stock/HBL directly. 2. Confirm the stock page identifies HBL. | The HBL stock-detail journey opens successfully. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/public/psx-terminal.spec.ts:52 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-009 | Stock Detail | Desktop Chrome · Anonymous | stock detail › resolves a lower-case ticker in the URL | HBL is a valid symbol. | 1. Open /stock/hbl. 2. Confirm the page resolves the ticker. | Lower-case ticker links resolve without a broken page. | Journey completed and all user-facing assertions passed. | Pass | P2 | frontend/packages/e2e/tests/public/psx-terminal.spec.ts:59 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-010 | Finance | Desktop Chrome · Demo user | finance transactions › adds a transaction and it appears in the list | Authenticated demo user on Finance. | 1. Open Transactions. 2. Add merchant E2E Test Merchant and PKR 1,234. 3. Save. 4. Verify the committed row. | The transaction is saved, the dialog closes, and the row appears. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/finance-crud.spec.ts:29 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-011 | Finance | Desktop Chrome · Demo user | finance transactions › the new transaction is findable by search | Authenticated demo user; transaction can be added. | 1. Add E2E Test Merchant. 2. Search for that merchant. | The newly added transaction remains visible in filtered results. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/finance-crud.spec.ts:53 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-012 | Finance | Desktop Chrome · Demo user | finance transactions › a search with no matches does not show the new transaction | Authenticated demo user; transaction can be added. | 1. Add E2E Test Merchant. 2. Search for zzzz-no-such-merchant. | The nonmatching transaction is excluded from results. | Journey completed and all user-facing assertions passed. | Pass | P2 | frontend/packages/e2e/tests/authed/finance-crud.spec.ts:69 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-013 | Finance | Desktop Chrome · Demo user | finance transactions › the add dialog rejects an empty amount rather than saving a zero row | Authenticated demo user on Finance. | 1. Open Add Transaction. 2. Enter a merchant but no amount. 3. Submit. | No zero-value transaction is created. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/finance-crud.spec.ts:83 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-014 | Finance | Pixel 7 · Demo user | finance transactions › adds a transaction and it appears in the list | Authenticated demo user on Finance. | 1. Open Transactions. 2. Add merchant E2E Test Merchant and PKR 1,234. 3. Save. 4. Verify the committed row. | The transaction is saved, the dialog closes, and the row appears. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/finance-crud.spec.ts:29 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-015 | Finance | Pixel 7 · Demo user | finance transactions › the new transaction is findable by search | Authenticated demo user; transaction can be added. | 1. Add E2E Test Merchant. 2. Search for that merchant. | The newly added transaction remains visible in filtered results. | User could not continue: a full-screen loading overlay intercepted the Finance tab interaction until the action timed out. | Fail | P1 | frontend/packages/e2e/tests/authed/finance-crud.spec.ts:53 | test-results/authed-finance-crud-financ-a10af-ction-is-findable-by-search-authed-mobile/video.webm test-results/authed-finance-crud-financ-a10af-ction-is-findable-by-search-authed-mobile/error-context.md test-results/authed-finance-crud-financ-a10af-ction-is-findable-by-search-authed-mobile/trace.zip | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-016 | Finance | Pixel 7 · Demo user | finance transactions › a search with no matches does not show the new transaction | Authenticated demo user; transaction can be added. | 1. Add E2E Test Merchant. 2. Search for zzzz-no-such-merchant. | The nonmatching transaction is excluded from results. | User could not continue: a full-screen loading overlay intercepted the Finance tab interaction until the action timed out. | Fail | P2 | frontend/packages/e2e/tests/authed/finance-crud.spec.ts:69 | test-results/authed-finance-crud-financ-58d95-ot-show-the-new-transaction-authed-mobile/video.webm test-results/authed-finance-crud-financ-58d95-ot-show-the-new-transaction-authed-mobile/error-context.md test-results/authed-finance-crud-financ-58d95-ot-show-the-new-transaction-authed-mobile/trace.zip | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-017 | Finance | Pixel 7 · Demo user | finance transactions › the add dialog rejects an empty amount rather than saving a zero row | Authenticated demo user on Finance. | 1. Open Add Transaction. 2. Enter a merchant but no amount. 3. Submit. | No zero-value transaction is created. | User could not continue: a full-screen loading overlay intercepted the Finance tab interaction until the action timed out. | Fail | P1 | frontend/packages/e2e/tests/authed/finance-crud.spec.ts:83 | test-results/authed-finance-crud-financ-ee76a-ther-than-saving-a-zero-row-authed-mobile/test-failed-1.png test-results/authed-finance-crud-financ-ee76a-ther-than-saving-a-zero-row-authed-mobile/video.webm test-results/authed-finance-crud-financ-ee76a-ther-than-saving-a-zero-row-authed-mobile/error-context.md test-results/authed-finance-crud-financ-ee76a-ther-than-saving-a-zero-row-authed-mobile/trace.zip | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-018 | Dashboard | Desktop Chrome · Demo user | dashboard › loads for the signed-in demo account | Valid demo session. | 1. Open /app. 2. Confirm the dashboard title and route. | The signed-in demo user reaches the dashboard without an auth bounce. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/navigation.spec.ts:20 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-019 | Dashboard | Desktop Chrome · Demo user | dashboard › mounts the AI recommendation card | Valid demo session; deterministic AI response enabled. | 1. Open /app. 2. Locate the recommendation card. | The recommendation surface is visible and does not break the dashboard. | Journey completed and all user-facing assertions passed. | Pass | P2 | frontend/packages/e2e/tests/authed/navigation.spec.ts:28 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-020 | Dashboard | Pixel 7 · Demo user | dashboard › loads for the signed-in demo account | Valid demo session. | 1. Open /app. 2. Confirm the dashboard title and route. | The signed-in demo user reaches the dashboard without an auth bounce. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/navigation.spec.ts:20 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-021 | Dashboard | Pixel 7 · Demo user | dashboard › mounts the AI recommendation card | Valid demo session; deterministic AI response enabled. | 1. Open /app. 2. Locate the recommendation card. | The recommendation surface is visible and does not break the dashboard. | Journey completed and all user-facing assertions passed. | Pass | P2 | frontend/packages/e2e/tests/authed/navigation.spec.ts:28 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-022 | Navigation | Desktop Chrome · Demo user | navigation sweep › reaches /app and it identifies itself | Valid demo session. | 1. Navigate directly to /app. 2. Confirm title and route. | Dashboard destination renders and identifies itself. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/navigation.spec.ts:38 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-023 | Navigation | Desktop Chrome · Demo user | navigation sweep › reaches /psx and it identifies itself | Valid demo session. | 1. Navigate directly to /psx. 2. Confirm title and route. | PSX destination renders and identifies itself. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/navigation.spec.ts:38 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-024 | Navigation | Desktop Chrome · Demo user | navigation sweep › reaches /portfolio and it identifies itself | Valid demo session. | 1. Navigate directly to /portfolio. 2. Confirm title and route. | Portfolio destination renders and identifies itself. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/navigation.spec.ts:38 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-025 | Navigation | Desktop Chrome · Demo user | navigation sweep › reaches /watchlist and it identifies itself | Valid demo session. | 1. Navigate directly to /watchlist. 2. Confirm title and route. | Watchlist destination renders and identifies itself. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/navigation.spec.ts:38 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-026 | Navigation | Desktop Chrome · Demo user | navigation sweep › reaches /finance and it identifies itself | Valid demo session. | 1. Navigate directly to /finance. 2. Confirm title and route. | Finance destination renders and identifies itself. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/navigation.spec.ts:38 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-027 | Navigation | Desktop Chrome · Demo user | navigation sweep › reaches /alerts and it identifies itself | Valid demo session. | 1. Navigate directly to /alerts. 2. Confirm title and route. | Alerts destination renders and identifies itself. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/navigation.spec.ts:38 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-028 | Navigation | Desktop Chrome · Demo user | navigation sweep › moves between routes without a full reload | Valid demo session on Dashboard. | 1. Open /app. 2. Select Finance in app navigation. 3. Confirm /finance. | Client-side navigation reaches Finance without a broken transition. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/navigation.spec.ts:46 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-029 | Navigation | Pixel 7 · Demo user | navigation sweep › reaches /app and it identifies itself | Valid demo session. | 1. Navigate directly to /app. 2. Confirm title and route. | Dashboard destination renders and identifies itself. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/navigation.spec.ts:38 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-030 | Navigation | Pixel 7 · Demo user | navigation sweep › reaches /psx and it identifies itself | Valid demo session. | 1. Navigate directly to /psx. 2. Confirm title and route. | PSX destination renders and identifies itself. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/navigation.spec.ts:38 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-031 | Navigation | Pixel 7 · Demo user | navigation sweep › reaches /portfolio and it identifies itself | Valid demo session. | 1. Navigate directly to /portfolio. 2. Confirm title and route. | Portfolio destination renders and identifies itself. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/navigation.spec.ts:38 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-032 | Navigation | Pixel 7 · Demo user | navigation sweep › reaches /watchlist and it identifies itself | Valid demo session. | 1. Navigate directly to /watchlist. 2. Confirm title and route. | Watchlist destination renders and identifies itself. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/navigation.spec.ts:38 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-033 | Navigation | Pixel 7 · Demo user | navigation sweep › reaches /finance and it identifies itself | Valid demo session. | 1. Navigate directly to /finance. 2. Confirm title and route. | Finance destination renders and identifies itself. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/navigation.spec.ts:38 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-034 | Navigation | Pixel 7 · Demo user | navigation sweep › reaches /alerts and it identifies itself | Valid demo session. | 1. Navigate directly to /alerts. 2. Confirm title and route. | Alerts destination renders and identifies itself. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/navigation.spec.ts:38 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-035 | Navigation | Pixel 7 · Demo user | navigation sweep › moves between routes without a full reload | Valid demo session on Dashboard. | 1. Open /app. 2. Select Finance in app navigation. 3. Confirm /finance. | Client-side navigation reaches Finance without a broken transition. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/navigation.spec.ts:46 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-036 | Portfolio | Desktop Chrome · Demo user | portfolio holdings › lists holdings with labelled edit and delete controls | Valid demo session with seeded holdings. | 1. Open /portfolio. 2. Locate accessible Edit and Delete controls. | Each holding can be managed through visible, labelled controls. | User could not start holding management: no visible Delete control was available within the expected 10 seconds. | Fail | P1 | frontend/packages/e2e/tests/authed/portfolio-crud.spec.ts:18 | test-results/authed-portfolio-crud-port-c9b8f-ed-edit-and-delete-controls-authed-chromium/test-failed-1.png test-results/authed-portfolio-crud-port-c9b8f-ed-edit-and-delete-controls-authed-chromium/video.webm test-results/authed-portfolio-crud-port-c9b8f-ed-edit-and-delete-controls-authed-chromium/error-context.md test-results/authed-portfolio-crud-port-c9b8f-ed-edit-and-delete-controls-authed-chromium/trace.zip | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-037 | Portfolio | Desktop Chrome · Demo user | portfolio holdings › deleting asks how, rather than removing immediately | Valid demo session with at least one holding. | 1. Open /portfolio. 2. Select Delete. 3. Inspect the decision dialog. | The holding remains until the user chooses Sold or Just remove it. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/portfolio-crud.spec.ts:27 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-038 | Portfolio | Desktop Chrome · Demo user | portfolio holdings › "Just remove it" drops the holding from the table | Valid demo session with at least one holding. | 1. Select Delete. 2. Choose Just remove it. 3. Recount holdings. | The selected holding is removed without entering a sale. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/portfolio-crud.spec.ts:43 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-039 | Portfolio | Desktop Chrome · Demo user | portfolio holdings › "I sold it" opens the sale form instead of deleting | Valid demo session with at least one holding. | 1. Select Delete. 2. Choose I sold it. 3. Inspect the next step. | A sale form opens and the holding remains until the sale is recorded. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/portfolio-crud.spec.ts:57 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-040 | Portfolio | Pixel 7 · Demo user | portfolio holdings › lists holdings with labelled edit and delete controls | Valid demo session with seeded holdings. | 1. Open /portfolio. 2. Locate accessible Edit and Delete controls. | Each holding can be managed through visible, labelled controls. | User could not start holding management: no visible Delete control was available within the expected 10 seconds. | Fail | P1 | frontend/packages/e2e/tests/authed/portfolio-crud.spec.ts:18 | test-results/authed-portfolio-crud-port-c9b8f-ed-edit-and-delete-controls-authed-mobile/video.webm test-results/authed-portfolio-crud-port-c9b8f-ed-edit-and-delete-controls-authed-mobile/error-context.md test-results/authed-portfolio-crud-port-c9b8f-ed-edit-and-delete-controls-authed-mobile/trace.zip | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-041 | Portfolio | Pixel 7 · Demo user | portfolio holdings › deleting asks how, rather than removing immediately | Valid demo session with at least one holding. | 1. Open /portfolio. 2. Select Delete. 3. Inspect the decision dialog. | The holding remains until the user chooses Sold or Just remove it. | User could not start holding management: no visible Delete control was available within the expected 10 seconds. | Fail | P1 | frontend/packages/e2e/tests/authed/portfolio-crud.spec.ts:27 | test-results/authed-portfolio-crud-port-768db-r-than-removing-immediately-authed-mobile/video.webm test-results/authed-portfolio-crud-port-768db-r-than-removing-immediately-authed-mobile/error-context.md test-results/authed-portfolio-crud-port-768db-r-than-removing-immediately-authed-mobile/trace.zip | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-042 | Portfolio | Pixel 7 · Demo user | portfolio holdings › "Just remove it" drops the holding from the table | Valid demo session with at least one holding. | 1. Select Delete. 2. Choose Just remove it. 3. Recount holdings. | The selected holding is removed without entering a sale. | User could not start holding management: no visible Delete control was available within the expected 10 seconds. | Fail | P1 | frontend/packages/e2e/tests/authed/portfolio-crud.spec.ts:43 | test-results/authed-portfolio-crud-port-3e67b--the-holding-from-the-table-authed-mobile/test-failed-1.png test-results/authed-portfolio-crud-port-3e67b--the-holding-from-the-table-authed-mobile/video.webm test-results/authed-portfolio-crud-port-3e67b--the-holding-from-the-table-authed-mobile/error-context.md test-results/authed-portfolio-crud-port-3e67b--the-holding-from-the-table-authed-mobile/trace.zip | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-043 | Portfolio | Pixel 7 · Demo user | portfolio holdings › "I sold it" opens the sale form instead of deleting | Valid demo session with at least one holding. | 1. Select Delete. 2. Choose I sold it. 3. Inspect the next step. | A sale form opens and the holding remains until the sale is recorded. | User could not start holding management: no visible Delete control was available within the expected 10 seconds. | Fail | P1 | frontend/packages/e2e/tests/authed/portfolio-crud.spec.ts:57 | test-results/authed-portfolio-crud-port-68ba0-le-form-instead-of-deleting-authed-mobile/test-failed-1.png test-results/authed-portfolio-crud-port-68ba0-le-form-instead-of-deleting-authed-mobile/video.webm test-results/authed-portfolio-crud-port-68ba0-le-form-instead-of-deleting-authed-mobile/error-context.md test-results/authed-portfolio-crud-port-68ba0-le-form-instead-of-deleting-authed-mobile/trace.zip | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-044 | Watchlist | Desktop Chrome · Demo user | watchlist › seeds a watchlist with labelled remove controls | Valid demo session. | 1. Open /watchlist. 2. Locate labelled Remove controls. | Seeded symbols and accessible removal actions are visible. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/watchlist-crud.spec.ts:18 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-045 | Watchlist | Desktop Chrome · Demo user | watchlist › removing a symbol drops it from the list | Valid demo session with seeded symbols. | 1. Capture a symbol. 2. Select its Remove action. 3. Verify it disappears. | Only the selected symbol is removed. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/watchlist-crud.spec.ts:27 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-046 | Watchlist | Desktop Chrome · Demo user | watchlist › removals accumulate rather than resetting between actions | Valid demo session with at least two symbols. | 1. Remove one symbol. 2. Remove a second symbol. 3. Verify both remain removed. | Successive removals persist during the journey. | Journey completed and all user-facing assertions passed. | Pass | P2 | frontend/packages/e2e/tests/authed/watchlist-crud.spec.ts:50 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-047 | Watchlist | Pixel 7 · Demo user | watchlist › seeds a watchlist with labelled remove controls | Valid demo session. | 1. Open /watchlist. 2. Locate labelled Remove controls. | Seeded symbols and accessible removal actions are visible. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/watchlist-crud.spec.ts:18 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-048 | Watchlist | Pixel 7 · Demo user | watchlist › removing a symbol drops it from the list | Valid demo session with seeded symbols. | 1. Capture a symbol. 2. Select its Remove action. 3. Verify it disappears. | Only the selected symbol is removed. | Journey completed and all user-facing assertions passed. | Pass | P1 | frontend/packages/e2e/tests/authed/watchlist-crud.spec.ts:27 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26
E2E-049 | Watchlist | Pixel 7 · Demo user | watchlist › removals accumulate rather than resetting between actions | Valid demo session with at least two symbols. | 1. Remove one symbol. 2. Remove a second symbol. 3. Verify both remain removed. | Successive removals persist during the journey. | Journey completed and all user-facing assertions passed. | Pass | P2 | frontend/packages/e2e/tests/authed/watchlist-crud.spec.ts:50 | reports/results.json | 50d88ee · tayyib | 2026-07-29 16:13:26

## Authentication
Test Case ID | Module | Test Scenario | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC-AUTH-01 | Authentication | Sign up with valid details | User is logged out and on the Auth page in Sign Up mode | 1. Enter First Name, Last Name 2. Enter valid email 3. Enter password (8+ chars, uppercase, number, special char) 4. Click Create Account | First Name=Ali, Last Name=Khan, Email=ali.khan+test1@nafaiq.test, Password=Passw0rd!23 | Account is created; confirmation email screen shown or user redirected to /app |  | Not Executed | P1
TC-AUTH-02 | Authentication | Sign up with password less than 8 characters | On Sign Up form with valid name/email entered | 1. Enter a short password 2. Click Create Account | Password=Ab1! | Error toast "Password must be at least 8 characters" shown; account not created |  | Not Executed | P1
TC-AUTH-03 | Authentication | Password strength meter updates live | On Sign Up form, password field focused | 1. Type password gradually adding uppercase, number, special character | Type: a -> Aa1 -> Aa1! -> Aa1!2345 | Strength label updates through Too weak -> Weak -> Fair -> Good -> Strong as rules are met |  | Not Executed | P3
TC-AUTH-04 | Authentication | Sign up with empty or single-character name | On Sign Up form | 1. Leave First/Last Name empty or 1 character 2. Fill rest of form 3. Click Create Account | First Name="" or "A" | Error toast "Please enter your name" shown; form not submitted |  | Not Executed | P2
TC-AUTH-05 | Authentication | Sign in with correct email and password | A verified account already exists | 1. Switch to Sign In mode 2. Enter correct email/password 3. Click Sign In | Email=ali.khan@nafaiq.test, Password=Passw0rd!23 | User logs in successfully, "Welcome back!" toast shown, redirected to /app |  | Not Executed | P1
TC-AUTH-06 | Authentication | Sign in with incorrect password | A verified account exists | 1. Enter registered email with wrong password 2. Click Sign In | Email=ali.khan@nafaiq.test, Password=WrongPass1! | Login fails; error toast with auth error message displayed |  | Not Executed | P1
TC-AUTH-07 | Authentication | Sign in using Google OAuth | A Google test account is available | 1. Click "Continue with Google" 2. Complete Google account selection | Google test account credentials | User is redirected back to /auth and signed in successfully |  | Not Executed | P2
TC-AUTH-08 | Authentication | Redirect to originally requested page after login | User is logged out | 1. Visit a protected route while logged out 2. Redirected to /auth?redirect=... 3. Log in | Target URL=/auth?redirect=/portfolio | User is redirected to /portfolio, not just /app |  | Not Executed | P3
TC-AUTH-09 | Authentication | Logout clears session | User is logged in | 1. Click Logout 2. Observe app state | N/A | Session/user cleared, demo/local data reset, redirected to login/landing page |  | Not Executed | P1
TC-AUTH-10 | Authentication | Access protected API without token | None | 1. Call a protected endpoint without Authorization header | GET /portfolio/list, no Authorization header | API returns HTTP 401 "Missing Authorization header" |  | Not Executed | P1
TC-AUTH-11 | Authentication | Access protected API with invalid/expired JWT | None | 1. Call protected endpoint with invalid/expired Bearer token | Authorization: Bearer invalid.expired.token | API returns HTTP 401 "Invalid token: ..." |  | Not Executed | P1
TC-AUTH-12 | Authentication | Sign up with an already registered email | An account already exists with the test email | 1. Enter an already-registered email 2. Fill rest of form 3. Click Create Account | Email=existing.user@nafaiq.test | Error toast shown indicating email already registered; no duplicate account |  | Not Executed | P2
TC-AUTH-13 | Authentication | Demo sign-in | On Auth page, logged out | 1. Choose Demo/Guest sign-in option | N/A | User enters app using demo session with sample data, no real credentials | Related automation confirms the Try Demo action is visible and uses a valid demo session, but the button click journey itself was not executed. | Not Executed | P3

## Dashboard
Test Case ID | Module | Test Scenario | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC-DASH-01 | Dashboard | Dashboard loads with personalized greeting | User logged in with display_name set in profile | 1. Log in 2. Land on Dashboard (/app) | display_name=Ali Khan | Dashboard displays greeting using user's first name |  | Not Executed | P2
TC-DASH-02 | Dashboard | New user redirected to plan selection | New user account with plan_selected_at = null | 1. Log in as new user 2. Land on Dashboard | N/A | User is automatically redirected to /plans before seeing dashboard |  | Not Executed | P1
TC-DASH-03 | Dashboard | KPI cards show correct values | User has existing portfolio holdings & finance transactions | 1. Open Dashboard | Known Net Worth/Portfolio Value/Total Invested/Monthly Spending figures | KPI cards display accurate values matching backend data |  | Not Executed | P1
TC-DASH-04 | Dashboard | Today P&L color coding | Portfolio with a holding whose price changed today | 1. Open Dashboard 2. Observe Today P&L card | Positive and negative P&L scenarios | Value shows bull(green) when positive, bear(red) when negative |  | Not Executed | P2
TC-DASH-05 | Dashboard | Portfolio chart range filter | User has portfolio history data available | 1. Click each range option 1M/3M/6M/1Y | Range options 1M/3M/6M/1Y | Chart re-renders with data for the selected range each time |  | Not Executed | P2
TC-DASH-06 | Dashboard | Quick Add Transaction from Dashboard | User logged in, on Dashboard | 1. Click Quick Add Transaction 2. Fill fields 3. Save | Merchant=Careem, Amount=500, Type=Expense, Category=Transport | Transaction saved; relevant KPI cards update accordingly |  | Not Executed | P1
TC-DASH-07 | Dashboard | Quick Add Holding from Dashboard | User logged in, on Dashboard | 1. Click Quick Add Holding 2. Search/select stock, enter shares/cost 3. Save | Symbol=HBL, Shares=50, Cost=120/share | Holding added to portfolio; Net Worth/Portfolio Value KPIs update |  | Not Executed | P1
TC-DASH-08 | Dashboard | Quick Add Alert from Dashboard | User logged in, on Dashboard | 1. Click Quick Add Alert 2. Choose type/details 3. Create | Type=Stock Price, Symbol=ENGRO, Condition=Above, Price=300 | Alert is created and appears under Alerts module |  | Not Executed | P2
TC-DASH-09 | Dashboard | Watchlist strip displays live data | At least 1 symbol added to watchlist | 1. Open Dashboard | Symbol=LUCK | Watchlist strip shows symbol with live/enriched price data |  | Not Executed | P2
TC-DASH-10 | Dashboard | Goals section displays up to 3 goals | User has 4+ goals created | 1. Open Dashboard | 4 goals with different targets | Only the first 3 goals are shown with saved/target amount and AI tip |  | Not Executed | P3
TC-DASH-11 | Dashboard | Macro widget shows economic indicators | Macro data available from backend | 1. Open Dashboard 2. Locate Macro widget | N/A | Policy Rate, Inflation and Exchange Rate values displayed correctly |  | Not Executed | P3
TC-DASH-12 | Dashboard | Toggle AI recommendation panel | Dashboard loaded with AI recommendation visible | 1. Click to hide panel 2. Click again to show | N/A | Panel visibility toggles as expected without page reload |  | Not Executed | P4
TC-DASH-13 | Dashboard | KSE-100 change percentage display | Market data feed available | 1. Open Dashboard 2. Observe KSE-100 change label | N/A | Percentage displays with + for gains, - for losses, or "--" when unavailable |  | Not Executed | P3
TC-DASH-14 | Dashboard | Demo mode shows showcase data | User entered app as demo/guest | 1. Open Dashboard | N/A | KPIs/charts use local showcase data instead of real backend calls | Related automation confirms the demo dashboard and recommendation card load on desktop/mobile, but it does not validate every showcase KPI or network-isolation claim. | Not Executed | P2

## Portfolio
Test Case ID | Module | Test Scenario | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC-PORT-01 | Portfolio | Add a new holding by searching stock | User logged in, on Portfolio page | 1. Click Add Holding 2. Search/select stock 3. Enter shares/cost 4. Save | Symbol=OGDC, Shares=100, Cost=95/share | New holding added to Holdings table with correct symbol, shares, cost basis |  | Not Executed | P1
TC-PORT-02 | Portfolio | Add holding with 0 or negative shares/cost | Add Holding modal open, stock selected | 1. Enter Shares=0 or negative, or Cost=0 or negative 2. Click Add Holding | Shares=0 / Cost=-50 (backend requires shares>0, avg_cost>0) | Validation error is shown; holding is not saved (API rejects with 422) |  | Not Executed | P1
TC-PORT-03 | Portfolio | Cost basis toggle - per share vs total | Add Holding modal open | 1. Switch between "Price per share" and "Total cost" 2. Enter values in each mode | Total Cost=50000 for 100 shares | Both modes accept input; total-cost mode shows computed per-share price |  | Not Executed | P2
TC-PORT-04 | Portfolio | Edit existing holding keeps symbol read-only | At least 1 holding exists | 1. Click Edit 2. Observe symbol field 3. Update shares/cost | New Shares=120, New Cost=98/share | Symbol read-only; shares/avg_cost/purchased_at editable and save correctly | Holding management could not be started reliably: the automated journey failed before editing because a visible Delete control was unavailable. | Fail | P2
TC-PORT-05 | Portfolio | Remove holding - choose Sold | At least 1 holding exists | 1. Click Remove 2. Choose "Sold" 3. Enter sell price/fees 4. Confirm | Sell Price=110/share, Fees=50 | Holding removed, sell transaction recorded, proceeds booked, realized P&L reflects sale | Desktop reached the sale form without prematurely deleting the holding. Pixel 7 could not start the flow because the Delete control was unavailable; final sale submission was not covered. | Fail | P1
TC-PORT-06 | Portfolio | Sell a holding at price 0 (worthless/delisted exit) | At least 1 holding exists for a delisted/worthless stock | 1. Click Remove 2. Choose "Sold" 3. Enter Price=0 4. Confirm | Sell Price=0, Fees=0 | Sale is accepted (price >= 0 allowed) and holding is closed out with 0 proceeds |  | Not Executed | P3
TC-PORT-07 | Portfolio | Remove holding - choose Remove (no sale) | At least 1 holding exists | 1. Click Remove 2. Choose "Remove" 3. Confirm | N/A | Holding/transactions deleted with no cash booked and no transaction entry | Desktop 'Just remove it' removed one holding. Pixel 7 could not start the flow because the Delete control was unavailable. | Fail | P1
TC-PORT-08 | Portfolio | Holdings table displays correct calculated values | Holding exists with known cost/shares | 1. Open Holdings table | Shares=100, Cost=95 | Shares, avg cost, current price, market value, P&L calculated accurately |  | Not Executed | P1
TC-PORT-09 | Portfolio | Net worth updates after holding changes | Existing Net Worth noted | 1. Add/remove a holding 2. Revisit Net Worth section | N/A | Total market value/cost basis update to reflect the change |  | Not Executed | P1
TC-PORT-10 | Portfolio | Portfolio history chart range change | Portfolio history data available | 1. Change history days range | 30/90/180/365 days | History chart reloads with data points matching selected range |  | Not Executed | P2
TC-PORT-11 | Portfolio | Allocation cards reflect holdings distribution | Holdings across multiple sectors | 1. Open Portfolio Allocation view | N/A | Allocation cards correctly reflect sector/asset distribution |  | Not Executed | P3
TC-PORT-12 | Portfolio | Add duplicate holding for same symbol | Symbol already held | 1. Attempt to add the same symbol again | Add HBL again (already held) | App shows a warning instead of silently creating a duplicate |  | Not Executed | P3
TC-PORT-13 | Portfolio | Transactions list reflects buy/sell history | At least 1 buy and 1 sell performed | 1. Open Portfolio Transactions | N/A | Both buy and sell transactions appear with correct type, qty, price, date |  | Not Executed | P2

## Notifications
Test Case ID | Module | Test Scenario | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC-NOTIF-01 | Notifications | Unread badge count is accurate | Mix of read/unread notifications exist | 1. Observe the bell icon badge | N/A | Badge displays correct count of unread notifications only |  | Not Executed | P1
TC-NOTIF-02 | Notifications | Notification dropdown opens on click | User logged in | 1. Click the notification bell icon | N/A | Dropdown opens showing most recent notifications |  | Not Executed | P1
TC-NOTIF-03 | Notifications | Clicking a notification marks it as read | At least 1 unread notification exists | 1. Open dropdown 2. Click an unread notification | N/A | Notification marked read; unread badge count decreases by one |  | Not Executed | P1
TC-NOTIF-04 | Notifications | Live KSE-100 notification appears | Real (non-demo) logged-in user, market data available | 1. Open notification dropdown | N/A | Live KSE-100 index change notification appears when data is available |  | Not Executed | P3
TC-NOTIF-05 | Notifications | Update notification preferences | On Settings > Notifications | 1. Toggle push/email preferences 2. Save | Push=On, Email=Off | Preferences saved and persist after reload/re-login |  | Not Executed | P2
TC-NOTIF-06 | Notifications | Notifications list loads via API | Authenticated user with token | 1. Call GET /notifications/list | GET /notifications/list | Returns notifications with correct fields (id, title, created_at, read, kind, link) |  | Not Executed | P1
TC-NOTIF-07 | Notifications | Demo user sees local notifications only | Logged in as demo user | 1. Trigger a local/demo alert event 2. Open notification bell | N/A | Notification list shows local Redux-based notifications, not backend ones |  | Not Executed | P2
TC-NOTIF-08 | Notifications | Notification link navigates correctly | A notification with a link exists | 1. Click a notification with an associated link | N/A | App navigates to the correct related page (e.g. /psx) |  | Not Executed | P3
TC-NOTIF-09 | Notifications | Empty notifications state | User with zero notifications | 1. Open notification bell | N/A | Dropdown shows appropriate empty state message |  | Not Executed | P4
TC-NOTIF-10 | Notifications | Mark notification as read via API | Valid notification_id exists | 1. Call PATCH /notifications/{id}/read | PATCH /notifications/{id}/read | Read status updates to true and reflected on next list fetch |  | Not Executed | P2

## Alerts
Test Case ID | Module | Test Scenario | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC-ALERT-01 | Alerts | Create Stock Price alert | On Alerts page | 1. Select Stock Price type 2. Choose stock, condition, price 3. Create | Symbol=HBL, Condition=Above, Price=150 | Alert created and appears in Active Alerts list with correct details |  | Not Executed | P1
TC-ALERT-02 | Alerts | Create Stock Price alert with invalid/negative price | Stock Price type selected | 1. Enter a negative/invalid price 2. Click Create | Price=-10 | Validation error shown (price must be >= 0); alert not created |  | Not Executed | P1
TC-ALERT-03 | Alerts | Create Bill Reminder alert | On Alerts page | 1. Select Bill Reminder type 2. Choose bill/timing 3. Create | Bill=Electricity Bill, Timing=3 days before due | Bill reminder alert is created and listed under Active Alerts |  | Not Executed | P2
TC-ALERT-04 | Alerts | Create Budget alert with preset and custom threshold | On Alerts page | 1. Select Budget type 2. Choose category 3. Select preset then custom % 4. Create | Category=Food, Preset=80%, Custom=65% | Alert saves with the selected threshold whether preset or custom |  | Not Executed | P2
TC-ALERT-05 | Alerts | Create Goal Milestone alert with preset and custom milestone | On Alerts page | 1. Select Goal Milestone type 2. Choose goal 3. Select preset then custom % 4. Create | Goal=Emergency Fund, Preset=50%, Custom=30% | Alert saves with the selected milestone whether preset or custom |  | Not Executed | P2
TC-ALERT-06 | Alerts | Push/Email notification toggles are independent | Creating any alert | 1. Toggle Push and Email in different combinations | Push=On/Email=Off and vice versa | Each toggle's state saved independently and reflected on the alert |  | Not Executed | P3
TC-ALERT-07 | Alerts | Backend rejects invalid alert type | None | 1. Send POST /alerts with type outside allowed values | type="invalid_type" | API returns validation error (422) since type must match allowed pattern |  | Not Executed | P2
TC-ALERT-08 | Alerts | Toggle an existing alert enabled/disabled | Existing alert present | 1. Toggle alert's enabled switch | PATCH /alerts/{alert_id} | Alert's enabled state updates immediately and persists on reload |  | Not Executed | P1
TC-ALERT-09 | Alerts | Delete an alert | Existing alert present | 1. Click delete 2. Confirm deletion | DELETE /alerts/{alert_id} | Alert removed from Active Alerts list; API returns deleted id |  | Not Executed | P1
TC-ALERT-10 | Alerts | Alerts Events list shows triggered history | Alert condition met/simulated | 1. Trigger/simulate alert 2. Open Alerts Events tab | /alerts/evaluate | Triggered alert event appears with correct details; can be marked as read |  | Not Executed | P2
TC-ALERT-11 | Alerts | Toggle/delete a non-existent alert | None | 1. Call PATCH/DELETE on a non-existent alert_id | alert_id=999999 | API returns HTTP 404 "Alert not found" |  | Not Executed | P2
TC-ALERT-12 | Alerts | Create Price Alert from stock detail page | On a stock's detail page | 1. Click price alert action (PriceAlertModal) 2. Set condition/price 3. Save | Condition=Below, Price=250 | Price alert created directly from stock page and appears in Alerts module |  | Not Executed | P3

## Finance
Test Case ID | Module | Test Scenario | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC-FIN-01 | Finance | Add a new expense transaction | User logged in, on Finance > Transactions tab | 1. Click Add Transaction 2. Enter merchant, amount, type=Expense, category, account 3. Save | Merchant=Foodpanda, Amount=850, Category=Food, Account=Cash | Transaction added and appears in list with correct details; balances update | Passed on Desktop Chrome and Pixel 7: transaction was added, the dialog closed, and the committed row appeared. | Pass | P1
TC-FIN-02 | Finance | Add a new income transaction | On Finance > Transactions tab | 1. Click Add Transaction 2. Set type=Income 3. Fill fields 4. Save | Merchant=Salary, Amount=150000, Category=Income | Income transaction saved and reflected in income/spending calculations |  | Not Executed | P1
TC-FIN-03 | Finance | Add transaction with zero or negative amount | On Add Transaction modal | 1. Enter Amount=0 or a negative value 2. Click Save | Amount=0 or Amount=-500 (backend requires amount > 0) | Validation error shown; transaction is not created (API rejects with 422) | Desktop empty-amount validation passed. Pixel 7 could not reach submission because a full-screen overlay blocked the Finance tab. | Fail | P1
TC-FIN-04 | Finance | Add a new payment method while creating a transaction | On Add Transaction modal | 1. Select "Add new payment method" 2. Type new account name 3. Save transaction | New Payment Method=Meezan Bank | New payment method created and available for future transactions |  | Not Executed | P3
TC-FIN-05 | Finance | Search/filter transactions list | Multiple transactions exist | 1. Type a merchant/category keyword into the search box | Search query="Foodpanda" | Only transactions matching the search term are displayed | Desktop positive/no-match searches passed. Pixel 7 search journeys were blocked by a full-screen loading overlay. | Fail | P3
TC-FIN-06 | Finance | Edit an existing transaction | At least one transaction exists | 1. Click Edit on a transaction 2. Change amount/category 3. Save | New Amount=1200 | Transaction updates with new values; totals recalculate |  | Not Executed | P2
TC-FIN-07 | Finance | Delete a single transaction | At least one transaction exists | 1. Click the delete icon on one specific transaction 2. Confirm | Delete one transaction, e.g. the Foodpanda entry | Only that transaction is removed; all other transactions remain unaffected |  | Not Executed | P1
TC-FIN-08 | Finance | Delete all transactions | At least one transaction exists | 1. Click Delete All button 2. Confirm in dialog | N/A | All transactions removed after confirmation; list shows empty state |  | Not Executed | P3
TC-FIN-09 | Finance | Create a monthly budget for a category | On Finance > Budgets tab | 1. Click Add Budget 2. Select category (excl. Income) 3. Enter limit 4. Save | Category=Shopping, Limit=15000 | Budget created; progress bar shows 0% spent against new limit |  | Not Executed | P1
TC-FIN-10 | Finance | Create budget with a negative limit amount | On Add Budget modal | 1. Enter Limit Amount as a negative value 2. Click Save | Limit Amount=-1000 (backend requires limit_amount >= 0) | Validation error shown; budget is not created |  | Not Executed | P2
TC-FIN-11 | Finance | Budget progress bar reflects spending | Budget exists for a category with logged transactions | 1. Add transactions under budgeted category 2. Open Budgets tab | Category=Shopping, Transaction Amount=5000 | Progress bar updates to reflect spent/limit ratio (e.g. ~33%) |  | Not Executed | P1
TC-FIN-12 | Finance | Edit an existing budget | A budget already exists for a category | 1. Click Edit on a budget 2. Change limit amount 3. Save | New Limit Amount=20000 | Budget updates with the new limit; progress bar recalculates against it |  | Not Executed | P2
TC-FIN-13 | Finance | Delete a single budget | At least one budget exists | 1. Click delete icon on one specific budget 2. Confirm | Delete the Shopping budget only | Only that budget is removed; other budgets remain unaffected |  | Not Executed | P2
TC-FIN-14 | Finance | Delete all budgets | At least one budget exists | 1. Click Delete All button on Budgets tab 2. Confirm | N/A | All budgets removed after confirmation; tab shows empty state |  | Not Executed | P3
TC-FIN-15 | Finance | Navigate budgets between months | On Budgets tab | 1. Click previous/next month arrows | N/A | Budget view updates to show the selected month's data correctly |  | Not Executed | P3
TC-FIN-16 | Finance | Add a bill with due date and recurring option | On Finance > Bills tab | 1. Click Add Bill 2. Enter name, amount, due date 3. Toggle Recurring 4. Save | Name=Electricity Bill, Amount=6500, Due Date=05-Aug-2026, Recurring=On | Bill added to list showing due date and recurring indicator |  | Not Executed | P1
TC-FIN-17 | Finance | Add a bill with zero or negative amount | On Add Bill modal | 1. Enter Amount=0 or a negative value 2. Click Save | Amount=0 or Amount=-200 (backend requires amount > 0) | Validation error shown; bill is not created |  | Not Executed | P2
TC-FIN-18 | Finance | Edit an existing bill | An unpaid bill exists | 1. Click Edit on a bill 2. Change amount or due date 3. Save | New Amount=7000, New Due Date=10-Aug-2026 | Bill updates with new values and reflects on the Bills list |  | Not Executed | P2
TC-FIN-19 | Finance | Mark a bill as paid | An unpaid bill exists | 1. Click "Mark as paid" on a bill | N/A | Bill status updates to paid; if recurring, due date rolls to next month |  | Not Executed | P1
TC-FIN-20 | Finance | Delete a single bill | At least one bill exists | 1. Click delete icon on one specific bill 2. Confirm | Delete the Electricity Bill only | Only that bill is removed; other bills remain unaffected |  | Not Executed | P2
TC-FIN-21 | Finance | Delete all bills | At least one bill exists | 1. Click Delete All button on Bills tab 2. Confirm | N/A | All bills removed after confirmation; tab shows empty state |  | Not Executed | P3
TC-FIN-22 | Finance | Create a savings goal | On Finance > Goals tab | 1. Click Add Goal 2. Enter name, target amount, target date 3. Save | Goal=Emergency Fund, Target=200000, Target Date=31-Dec-2026 | Goal is created and listed with 0% progress toward the target |  | Not Executed | P1
TC-FIN-23 | Finance | Create goal with zero or negative target amount | On Add Goal modal | 1. Enter Target=0 or negative value 2. Click Save | Target=0 or Target=-5000 (backend requires target > 0) | Validation error shown; goal is not created |  | Not Executed | P2
TC-FIN-24 | Finance | Contribute an amount toward a goal | At least one goal exists | 1. Click Contribute on a goal 2. Enter contribution amount 3. Save | Contribution=10000 | Saved amount increases by the contribution; progress % updates correctly |  | Not Executed | P1
TC-FIN-25 | Finance | Delete a single goal | At least one goal exists | 1. Click delete icon on one specific goal 2. Confirm | Delete the Emergency Fund goal only | Only that goal is removed; other goals remain unaffected |  | Not Executed | P2
TC-FIN-26 | Finance | Delete all goals | At least one goal exists | 1. Click Delete All button on Goals tab 2. Confirm | N/A | All goals removed after confirmation; tab shows empty state |  | Not Executed | P3
TC-FIN-27 | Finance | Zakat calculator computes zakat due above nisab | On Zakat tool, live gold/silver rates available | 1. Enter asset values 2. Enter liabilities 3. Select nisab source (gold/silver) | Cash=500000, Gold=5 tola, Liabilities=50000, Nisab Source=Silver | Zakatable wealth = assets - liabilities; if above nisab, Zakat Due = wealth x 2.5% |  | Not Executed | P2
TC-FIN-28 | Finance | Zakat calculator shows not liable when below nisab | On Zakat tool | 1. Enter low asset values so wealth is below nisab value | Cash=10000, Gold=0, Liabilities=0 | Zakat Due = 0 and above-nisab indicator shows false/not liable |  | Not Executed | P3
TC-FIN-29 | Finance | Export Zakat calculation as PDF | A Zakat calculation has been completed | 1. Click Export/Download PDF option | N/A | A PDF summarizing the Zakat calculation is generated and downloaded |  | Not Executed | P4

## Watchlist
Test Case ID | Module | Test Scenario | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC-WATCH-01 | Watchlist | Add a stock to Watchlist | User logged in, on Watchlist page | 1. Click Add Stock 2. Search symbol and select 3. Confirm | Symbol=PSO | Stock added and appears in Watchlist with live price data |  | Not Executed | P1
TC-WATCH-02 | Watchlist | Add an unknown/invalid symbol to Watchlist | On Watchlist page, Add Stock modal open | 1. Type a symbol that does not exist on PSX 2. Attempt to confirm | Symbol=XYZ123 (not a valid PSX ticker) | App rejects the symbol / shows an error since it fails the known-symbol check |  | Not Executed | P2
TC-WATCH-03 | Watchlist | Remove a stock from Watchlist | Watchlist has at least one stock | 1. Click remove/delete icon next to a stock | Symbol=PSO | Stock removed from Watchlist immediately | Passed on Desktop Chrome and Pixel 7: the selected labelled symbol disappeared and the list count decreased by one. | Pass | P1
TC-WATCH-04 | Watchlist | Prevent adding duplicate stock to Watchlist | A stock already exists in Watchlist | 1. Attempt to add the same symbol again | Symbol already in watchlist=HBL | App shows message that stock is already in watchlist; no duplicate created |  | Not Executed | P2
TC-WATCH-05 | Watchlist | Watchlist shows live price and daily change | Watchlist has at least one stock | 1. Open Watchlist page 2. Observe price and % change columns | N/A | Current price/daily change % shown and update, with correct bull/bear color |  | Not Executed | P1
TC-WATCH-06 | Watchlist | Create price alert directly from Watchlist | On Watchlist page with at least one stock | 1. Click alert/bell icon next to a stock 2. Set condition/price 3. Save | Symbol=ENGRO, Condition=Above, Price=320 | Price alert created and visible under Alerts module |  | Not Executed | P2
TC-WATCH-07 | Watchlist | Clear entire watchlist | Watchlist has at least 2 symbols | 1. Click the Delete All (clear) button 2. Confirm in dialog | N/A | All symbols are removed and Watchlist shows empty state |  | Not Executed | P3
TC-WATCH-08 | Watchlist | Empty watchlist state | Watchlist has zero stocks | 1. Open Watchlist page | N/A | Appropriate empty state/message shown with prompt to add a stock |  | Not Executed | P4
TC-WATCH-09 | Watchlist | Navigate to stock detail from Watchlist | Watchlist has at least one stock | 1. Click on a stock row/name in Watchlist | Symbol=LUCK | User navigated to that stock's detail page (/stock/LUCK) |  | Not Executed | P2
TC-WATCH-10 | Watchlist | Watchlist accessible for demo users | Logged in as demo/guest user | 1. Open Watchlist page 2. Add a sample stock | Symbol=OGDC | Demo watchlist works using local/sample data without a real account |  | Not Executed | P3

## AI Assistant
Test Case ID | Module | Test Scenario | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC-AI-01 | AI Assistant | Send a text message to AI Assistant | On Assistant panel, user logged in | 1. Type a question in chat box 2. Press send | "What is my current net worth?" | AI responds with a relevant, correctly formatted answer based on user's data |  | Not Executed | P1
TC-AI-02 | AI Assistant | AI proposes an add_transaction action | On Assistant panel | 1. Type a request implying a transaction 2. Send | "I spent 500 on groceries today" | Action Draft Card appears pre-filled with type, amount, category etc. for confirmation |  | Not Executed | P1
TC-AI-03 | AI Assistant | Confirm a proposed action | An Action Draft Card is shown | 1. Review pre-filled fields 2. Click Confirm | N/A | Proposed transaction is created in Finance module; success message shown |  | Not Executed | P1
TC-AI-04 | AI Assistant | Cancel a proposed action | An Action Draft Card is shown | 1. Click Cancel on the draft card | N/A | No transaction/data created; draft card is dismissed |  | Not Executed | P2
TC-AI-05 | AI Assistant | Edit a field before confirming an action | Action Draft Card shown with pre-filled amount | 1. Change amount field 2. Click Confirm | Change Amount from 500 to 750 | Action created using the edited value, not the original AI-suggested value |  | Not Executed | P2
TC-AI-06 | AI Assistant | AI prompts for missing required field | AI proposes an action missing a required field | 1. Observe Action Draft Card | N/A | Missing field is highlighted/required before Confirm can be used |  | Not Executed | P2
TC-AI-07 | AI Assistant | Use voice input via mic button | Microphone permission granted, on Assistant panel | 1. Click Mic button 2. Speak a query 3. Stop recording | Spoken: "Show my portfolio performance" | Speech is transcribed accurately into chat input and sent to assistant |  | Not Executed | P3
TC-AI-08 | AI Assistant | Mic button without microphone permission | Microphone permission denied/blocked | 1. Click Mic button | N/A | App shows a clear message that microphone access is required |  | Not Executed | P3
TC-AI-09 | AI Assistant | AI Assistant handles unrelated/out-of-scope question | On Assistant panel | 1. Ask an unrelated question | "What's the weather today?" | AI responds appropriately without crashing or hallucinating finance data |  | Not Executed | P3
TC-AI-10 | AI Assistant | Chat history persists within session | User has sent multiple messages | 1. Send 2-3 messages 2. Scroll up | N/A | Previous messages remain visible in correct order within the same session |  | Not Executed | P4

## Learn Hub
Test Case ID | Module | Test Scenario | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC-LEARN-01 | Learn Hub | Learn Hub loads available lessons | User logged in, on Learn Hub page | 1. Open Learn Hub | N/A | List of lessons/courses displayed with titles and completion status |  | Not Executed | P1
TC-LEARN-02 | Learn Hub | Completion ring reflects progress | User has completed some lessons | 1. Open Learn Hub 2. Observe completion ring/stat pill | e.g. 3 of 10 lessons completed | Completion ring shows accurate percentage matching completed lesson count |  | Not Executed | P2
TC-LEARN-03 | Learn Hub | Open and view a reading-type lesson | A reading-type lesson exists | 1. Click on a lesson 2. View ReadingView content | N/A | Lesson content renders correctly with readable formatting |  | Not Executed | P2
TC-LEARN-04 | Learn Hub | Watch a video lesson | A video-type lesson exists | 1. Open a video lesson 2. Play via VideoPlayer | N/A | Video plays correctly with standard playback controls |  | Not Executed | P2
TC-LEARN-05 | Learn Hub | Take a quiz and view results | A lesson with a quiz exists | 1. Complete quiz questions 2. Submit | Sample answers (mix of correct/incorrect) | ResultsView shows score and correct/incorrect breakdown accurately |  | Not Executed | P1
TC-LEARN-06 | Learn Hub | Financial vocabulary flashcards | On Learn Hub, flashcard feature available | 1. Open Flashcard Modal 2. Flip through terms | e.g. "Diversification", "Bull Market" | Flashcards display term/definition correctly, navigable forward/back |  | Not Executed | P2
TC-LEARN-07 | Learn Hub | Lesson marked complete after finishing | User is partway through a lesson | 1. Complete all required steps/quiz of a lesson | N/A | Lesson status updates to Completed and reflected in completion ring |  | Not Executed | P1
TC-LEARN-08 | Learn Hub | Related lessons suggested after completion | A lesson has just been completed | 1. Finish a lesson 2. View LessonSummaryCard/RelatedLessons | N/A | Relevant related lessons suggested based on completed topic |  | Not Executed | P3
TC-LEARN-09 | Learn Hub | Ask a question via lesson Chat Panel | On an active lesson page | 1. Open Chat Panel 2. Ask a question about lesson content | "What does diversification mean?" | Assistant responds with contextual help relevant to current lesson |  | Not Executed | P3
TC-LEARN-10 | Learn Hub | Resume a lesson from where left off | User previously exited a lesson midway | 1. Re-open the same lesson | N/A | Lesson resumes at last viewed section/step, not from the beginning |  | Not Executed | P3

## Market
Test Case ID | Module | Test Scenario | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC-MKT-01 | Market | KSE-100 index overview displays correctly | Market data feed available | 1. Open Market/PSX page 2. View Index Overview card | N/A | Current KSE-100 value, change points and % displayed with correct color coding |  | Not Executed | P1
TC-MKT-02 | Market | Market movers (gainers/losers) list | Market data available | 1. Open Market page 2. View Movers card | N/A | Top gainers/losers listed with accurate % change, sorted correctly |  | Not Executed | P1
TC-MKT-03 | Market | Sector heatmap displays sector performance | Market data available | 1. Open Market page 2. View Sector Heatmap | N/A | Sectors color-coded (green/red) proportional to day's performance |  | Not Executed | P2
TC-MKT-04 | Market | Stock screener filters results | On Market page, Screener card visible | 1. Apply a filter 2. View results | Sector=Banking | Screener returns only stocks matching the applied filter criteria |  | Not Executed | P2
TC-MKT-05 | Market | News feed shows latest market news | Market page loaded | 1. Scroll to News Feed section | N/A | Latest relevant news displayed with source and timestamp |  | Not Executed | P3
TC-MKT-06 | Market | Unusual activity widget flags abnormal moves | A stock has unusual activity for the day | 1. Open Market page 2. View Unusual Activity widget | N/A | Stocks with unusual volume/price movement listed with relevant metrics |  | Not Executed | P3
TC-MKT-07 | Market | Market ticker scrolls live prices | Market page loaded | 1. Observe the Market Ticker bar | N/A | Ticker continuously scrolls showing live/updated prices for key symbols |  | Not Executed | P3
TC-MKT-08 | Market | Click a stock from Market page opens detail page | On Market page with stock list visible | 1. Click on a stock symbol/row | Symbol=FFC | Navigates to stock detail page showing price, chart and fundamentals |  | Not Executed | P2
TC-MKT-09 | Market | Currency converter calculates correctly | On Currency tool, live exchange rates available | 1. Enter amount 2. Select From/To currencies | Amount=100, From=USD, To=PKR | Converted amount calculated correctly using current live exchange rate |  | Not Executed | P2
TC-MKT-10 | Market | Currency converter handles rate refresh | On Currency tool | 1. Click refresh/live-refresh option | N/A | Exchange rate updates to latest value; conversion recalculates automatically |  | Not Executed | P4
TC-MKT-11 | Market | Market Brief (AI-generated summary) displays | Market page loaded, AI market brief available | 1. Open Market page 2. View Market Brief card | N/A | Concise AI-generated summary of the day's market activity is shown |  | Not Executed | P3

## Reports
Test Case ID | Module | Test Scenario | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC-REP-01 | Reports | Generate an AI report for the first time | User logged in, no report generated yet | 1. Navigate to Reports/AI Insights 2. Click Generate Report | N/A | Loading state shown, then complete report renders with sections, metrics, citations |  | Not Executed | P1
TC-REP-02 | Reports | Regenerate an existing report | A report has already been generated | 1. Click Regenerate button | N/A | A fresh report is generated and replaces the previous one |  | Not Executed | P2
TC-REP-03 | Reports | Report generation error is handled gracefully | Simulate a backend/report generation failure | 1. Trigger report generation while service is unavailable | N/A | Error state with clear message and Retry button shown instead of crash/blank screen |  | Not Executed | P1
TC-REP-04 | Reports | Retry after a failed report generation | Report generation previously failed | 1. Click Retry on error state | N/A | Report generation attempted again and succeeds once issue is resolved |  | Not Executed | P2
TC-REP-05 | Reports | Report displays citations correctly | A report generated with citation data | 1. Open report 2. Scroll to citations section | N/A | Citations listed with correct source references matching report content |  | Not Executed | P3
TC-REP-06 | Reports | Report metrics render with correct values | Report generated for stock/portfolio with known data | 1. View metric pills within a report | N/A | Metric values (e.g. P/E, growth %) match underlying data accurately |  | Not Executed | P2
TC-REP-07 | Reports | Dashboard AI recommendation uses shared report component | Dashboard AI recommendation panel visible | 1. Open Dashboard 2. View AI recommendation content | N/A | Recommendation renders using same AiReportView format without layout errors |  | Not Executed | P3
TC-REP-08 | Reports | Report is accessible for demo users | Logged in as demo/guest user | 1. Attempt to generate/view an AI report | N/A | Demo user sees sample/placeholder report, or an appropriate message |  | Not Executed | P3

## User Profile
Test Case ID | Module | Test Scenario | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC-PROF-01 | User Profile | Update display name | User logged in, on Settings page | 1. Edit display name field 2. Save | Display Name=Ali Khan | Profile display name updates and reflects in Dashboard greeting/header |  | Not Executed | P1
TC-PROF-02 | User Profile | Toggle app theme (Light/Dark/System) | On Settings page | 1. Select Light, then Dark, then System | N/A | App appearance updates immediately for each option and persists after reload |  | Not Executed | P2
TC-PROF-03 | User Profile | Switch app language (English/Urdu) | On Settings page | 1. Toggle language to Urdu 2. Toggle back to English | N/A | UI text switches to Urdu correctly, then back to English, no layout breaking |  | Not Executed | P2
TC-PROF-04 | User Profile | Update notification preferences from Settings | On Settings > Notifications section | 1. Toggle push/email/SMS preferences 2. Save | Push=On, Email=Off, SMS=On | Preferences saved and persist after logout/login |  | Not Executed | P2
TC-PROF-05 | User Profile | Connect Gmail for auto bank transaction import | On Settings > Email Integration, user logged in | 1. Click Connect Gmail 2. Complete OAuth consent | Test Gmail account | Gmail account connects successfully; success toast confirms connection |  | Not Executed | P2
TC-PROF-06 | User Profile | Sync Gmail transactions manually | Gmail is already connected | 1. Click "Sync now" | N/A | New bank transaction emails are parsed and imported as transactions |  | Not Executed | P2
TC-PROF-07 | User Profile | Disconnect Gmail integration | Gmail is currently connected | 1. Click Disconnect | N/A | Gmail integration removed; success message confirms disconnection |  | Not Executed | P2
TC-PROF-08 | User Profile | Currency field is fixed to PKR | On Settings > Finance Settings | 1. Look for a currency selector | N/A | No currency selector available; currency fixed/displayed as PKR only |  | Not Executed | P4
TC-PROF-09 | User Profile | Cancel Gmail connection mid-flow | On Settings, Connect Gmail clicked | 1. Start Google OAuth flow 2. Cancel/close consent popup | N/A | App shows "Gmail connection cancelled" message; no broken connection state |  | Not Executed | P3
TC-PROF-10 | User Profile | Sync fails when Gmail token expired | Gmail connected but token expired/revoked | 1. Click "Sync now" | N/A | App shows a clear sync error message instead of failing silently |  | Not Executed | P2